## Sheet1
Description of Items | Unit | Area/Quantity | Rate per Unit | Estimated Cost in Taka
Soil Test & digital survey | L.S |  |  | 900000
Internal Road for Main Park | Sft/Sqm | 46888.13/4356.01 | 2750 | 11979000
Pavement tiles of size 300 mm x 300 mm | Sqm | 4356.01 | 2081 | 9064856.81
Providing clay wall tile facing strips | Sft/Sqm | 16533.99/1536.05 | 2542 | 3905000
Silicon based water repellent | Sft/Sqm | 16533.99/1536.05 | 226 | 347000
Semi-Permanent Structure | Sft/Sqm | 3562.58/330.97 | 11250 | 3723000
Site Development | Sft/Cft | 46888.13/468881.25 | 302 | 4010000
Mechanical Compaction of Earth | Sft/Cft | 46888.13/468881.25 | 418 | 5550000
For RCC/Bricks Bench | Nos | 40 | 35000 | 1400000
For Public toilet (Male & Female combined) | Nos | 4 | 2515729.26 | 10062917.04
For 4 nos Deep-Tube well (75mm x 150mm) | Nos | 4 | 753616 | 3014464
Kids Equipment dolna and slipper | L.S |  |  | 1000000
RCC Bridge Length=152.00 Meter | Meter | 152 | 1700000 | 258400000
River Bank Protective work 1660.00 m | Meter | 1660 | 59674.13 | 99059055.8
External Water Supply
I. Pump House | L.S |  |  | 600000
II. Distribution Pipe Line | L.S |  |  | 1000000
III. UGWR-10000 Gallon | Nos | 4 | 926867 | 3707000
External Electrification and Electro-Mechanical Components | L.S |  |  | 35300000
Construction of Compound drain | Rm | 1500 | 2760 | 4140000
Arboriculture | L.S |  |  | 2000000
459162293.65